## Risk Register
risk_id | risk_title | risk_statement_cause_event_impact | category | business_process_value_stream_optional | team_department | owner_accountable | raised_date | next_review_date | status | decision | acceptance_rationale_required_if_accept | financial_impact_1_5 | customer_service_impact_1_5 | operational_delivery_impact_1_5 | legal_regulatory_impact_1_5 | reputation_impact_1_5 | health_safety_impact_1_5 | overall_impact_calc | likelihood_1_5_12_month_horizon | inherent_score_calc | inherent_band_calc | key_controls_ids_or_short_list | control_effectiveness_1_5 | reduction_calc | residual_score_calc | residual_band_calc | risk_velocity_optional | confidence_optional | treatment_plan_summary | actions_link_jira_servicenow_etc | due_date | completion | latest_update_note | last_updated_date | updated_by
RSK-1001 | Single-sourced payment processor outage | Cause: reliance on one payment processor Event: extended processor outage Impact: inability to take customer payments | Operational | Order to Cash | Finance Operations | risk.owner@example.com | 2026-01-10 | 2026-07-10 | Open | Treat |  | 4 | 4 | 3 | 2 | 3 | 1 | 2.83 | 2 | 5.67 | Moderate | CTRL-PAY-01 | 3 | 0.36 | 3.63 | Low | Fast | High | Add secondary payment processor | JIRA-4501 | 2026-04-01 | 30% | Vendor evaluation in progress | 2026-02-05 | risk.manager@example.com
RSK-1002 | Unpatched internet-facing servers | Cause: delayed patch cycle Event: exploitation of known vulnerability Impact: data breach | Cyber & Information Security | IT Operations | Information Security | risk.manager@example.com | 2025-11-20 | 2026-05-20 | Open | Treat |  | 5 | 3 | 3 | 5 | 5 | 1 | 3.67 | 3 | 11 | Moderate | CTRL-SEC-04, CTRL-SEC-07 | 2 | 0.24 | 8.36 | Moderate | Fast | High | Automate patch management pipeline | SNOW-8821 | 2026-03-15 | 60% | Automated scanning enabled on 80% of estate | 2026-02-10 | risk.manager@example.com
RSK-1003 | Key engineering talent concentration | Cause: single engineer owns core billing system Event: departure without knowledge transfer Impact: extended delivery delays | People & Culture | Product Delivery | Engineering | risk.owner@example.com | 2025-09-01 | 2026-03-01 | Monitoring | Treat |  | 2 | 2 | 4 | 1 | 1 | 1 | 1.83 | 2 | 3.67 | Low | CTRL-PPL-02 | 2 | 0.24 | 2.79 | Low | Slow | Medium | Cross-train two additional engineers | JIRA-3390 | 2026-05-01 | 10% | Cross-training plan drafted | 2026-01-20 | risk.owner@example.com
RSK-1004 | Upcoming data-residency regulation | Cause: new regional data-residency law Event: non-compliance at enforcement date Impact: regulatory fines and forced re-architecture | Legal & Regulatory | Data Platform | Legal & Compliance | risk.manager@example.com | 2026-01-05 | 2026-04-05 | Open | Treat |  | 4 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 12 | High | CTRL-LEG-01 | 1 | 0.12 | 10.56 | Moderate | Medium | High | Data residency compliance program | JIRA-4602 | 2026-03-30 | 15% | Legal assessment underway | 2026-02-01 | risk.manager@example.com
RSK-1005 | Cloud hosting cost overrun | Cause: unbounded auto-scaling configuration Event: unexpected traffic spike Impact: budget overrun | Financial | Cloud Platform | Finance Operations | risk.owner@example.com | 2025-12-01 | 2026-06-01 | Closed | Accept | Cost capped by new billing alerts; residual exposure within appetite | 3 | 1 | 1 | 1 | 1 | 1 | 1.33 | 2 | 2.67 | Low | CTRL-FIN-03 | 4 | 0.48 | 1.39 | Low | Slow | High | Billing alerts and scaling caps implemented | JIRA-4210 | 2026-01-15 | 100% | Controls implemented and verified effective | 2026-01-16 | risk.owner@example.com
RSK-1006 | Unpatched internet-facing servers (variant 6) | Cause: delayed patch cycle Event: exploitation of known vulnerability Impact: data breach | Cyber & Information Security | IT Operations | Information Security | risk.manager@example.com | 2025-11-20 | 2026-05-20 | Open | Treat |  | 2 | 3 | 3 | 5 | 5 | 1 | 3.67 | 3 | 11 | Moderate | CTRL-SEC-04, CTRL-SEC-07 | 2 | 0.24 | 8.36 | Moderate | Fast | High | Automate patch management pipeline | SNOW-8821 | 2026-03-15 | 60% | Automated scanning enabled on 80% of estate | 2026-02-10 | risk.manager@example.com
RSK-1007 | Key engineering talent concentration (variant 7) | Cause: single engineer owns core billing system Event: departure without knowledge transfer Impact: extended delivery delays | Third Party & Vendor | Product Delivery | Engineering | risk.owner@example.com | 2025-09-01 | 2026-03-01 | Monitoring | Treat |  | 5 | 2 | 4 | 1 | 1 | 1 | 1.83 | 2 | 3.67 | Low | CTRL-PPL-02 | 2 | 0.24 | 2.79 | Low | Slow | Medium | Cross-train two additional engineers | JIRA-3390 | 2026-05-01 | 10% | Cross-training plan drafted | 2026-01-20 | risk.owner@example.com
RSK-1008 | Upcoming data-residency regulation (variant 8) | Cause: new regional data-residency law Event: non-compliance at enforcement date Impact: regulatory fines and forced re-architecture | Strategic | Data Platform | Legal & Compliance | risk.manager@example.com | 2026-01-05 | 2026-04-05 | Open | Treat |  | 3 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 12 | High | CTRL-LEG-01 | 1 | 0.12 | 10.56 | Moderate | Medium | High | Data residency compliance program | JIRA-4602 | 2026-03-30 | 15% | Legal assessment underway | 2026-02-01 | risk.manager@example.com
RSK-1009 | Cloud hosting cost overrun (variant 9) | Cause: unbounded auto-scaling configuration Event: unexpected traffic spike Impact: budget overrun | Financial | Cloud Platform | Finance Operations | risk.owner@example.com | 2025-12-01 | 2026-06-01 | Closed | Accept | Cost capped by new billing alerts; residual exposure within appetite | 3 | 1 | 1 | 1 | 1 | 1 | 1.33 | 2 | 2.67 | Low | CTRL-FIN-03 | 4 | 0.48 | 1.39 | Low | Slow | High | Billing alerts and scaling caps implemented | JIRA-4210 | 2026-01-15 | 100% | Controls implemented and verified effective | 2026-01-16 | risk.owner@example.com
RSK-1010 | Single-sourced payment processor outage (variant 10) | Cause: reliance on one payment processor Event: extended processor outage Impact: inability to take customer payments | Operational | Order to Cash | Finance Operations | risk.owner@example.com | 2026-01-10 | 2026-07-10 | Open | Treat |  | 5 | 4 | 3 | 2 | 3 | 1 | 2.83 | 2 | 5.67 | Moderate | CTRL-PAY-01 | 3 | 0.36 | 3.63 | Low | Fast | High | Add secondary payment processor | JIRA-4501 | 2026-04-01 | 30% | Vendor evaluation in progress | 2026-02-05 | risk.manager@example.com
RSK-1011 | Unpatched internet-facing servers (variant 11) | Cause: delayed patch cycle Event: exploitation of known vulnerability Impact: data breach | Cyber & Information Security | IT Operations | Information Security | risk.manager@example.com | 2025-11-20 | 2026-05-20 | Open | Treat |  | 2 | 3 | 3 | 5 | 5 | 1 | 3.67 | 3 | 11 | Moderate | CTRL-SEC-04, CTRL-SEC-07 | 2 | 0.24 | 8.36 | Moderate | Fast | High | Automate patch management pipeline | SNOW-8821 | 2026-03-15 | 60% | Automated scanning enabled on 80% of estate | 2026-02-10 | risk.manager@example.com
RSK-1012 | Key engineering talent concentration (variant 12) | Cause: single engineer owns core billing system Event: departure without knowledge transfer Impact: extended delivery delays | Third Party & Vendor | Product Delivery | Engineering | risk.owner@example.com | 2025-09-01 | 2026-03-01 | Monitoring | Treat |  | 5 | 2 | 4 | 1 | 1 | 1 | 1.83 | 2 | 3.67 | Low | CTRL-PPL-02 | 2 | 0.24 | 2.79 | Low | Slow | Medium | Cross-train two additional engineers | JIRA-3390 | 2026-05-01 | 10% | Cross-training plan drafted | 2026-01-20 | risk.owner@example.com
RSK-1013 | Upcoming data-residency regulation (variant 13) | Cause: new regional data-residency law Event: non-compliance at enforcement date Impact: regulatory fines and forced re-architecture | Strategic | Data Platform | Legal & Compliance | risk.manager@example.com | 2026-01-05 | 2026-04-05 | Open | Treat |  | 3 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 12 | High | CTRL-LEG-01 | 1 | 0.12 | 10.56 | Moderate | Medium | High | Data residency compliance program | JIRA-4602 | 2026-03-30 | 15% | Legal assessment underway | 2026-02-01 | risk.manager@example.com
RSK-1014 | Cloud hosting cost overrun (variant 14) | Cause: unbounded auto-scaling configuration Event: unexpected traffic spike Impact: budget overrun | Financial | Cloud Platform | Finance Operations | risk.owner@example.com | 2025-12-01 | 2026-06-01 | Closed | Accept | Cost capped by new billing alerts; residual exposure within appetite | 3 | 1 | 1 | 1 | 1 | 1 | 1.33 | 2 | 2.67 | Low | CTRL-FIN-03 | 4 | 0.48 | 1.39 | Low | Slow | High | Billing alerts and scaling caps implemented | JIRA-4210 | 2026-01-15 | 100% | Controls implemented and verified effective | 2026-01-16 | risk.owner@example.com
RSK-1015 | Single-sourced payment processor outage (variant 15) | Cause: reliance on one payment processor Event: extended processor outage Impact: inability to take customer payments | Operational | Order to Cash | Finance Operations | risk.owner@example.com | 2026-01-10 | 2026-07-10 | Open | Treat |  | 5 | 4 | 3 | 2 | 3 | 1 | 2.83 | 2 | 5.67 | Moderate | CTRL-PAY-01 | 3 | 0.36 | 3.63 | Low | Fast | High | Add secondary payment processor | JIRA-4501 | 2026-04-01 | 30% | Vendor evaluation in progress | 2026-02-05 | risk.manager@example.com
RSK-1016 | Unpatched internet-facing servers (variant 16) | Cause: delayed patch cycle Event: exploitation of known vulnerability Impact: data breach | Cyber & Information Security | IT Operations | Information Security | risk.manager@example.com | 2025-11-20 | 2026-05-20 | Open | Treat |  | 2 | 3 | 3 | 5 | 5 | 1 | 3.67 | 3 | 11 | Moderate | CTRL-SEC-04, CTRL-SEC-07 | 2 | 0.24 | 8.36 | Moderate | Fast | High | Automate patch management pipeline | SNOW-8821 | 2026-03-15 | 60% | Automated scanning enabled on 80% of estate | 2026-02-10 | risk.manager@example.com
RSK-1017 | Key engineering talent concentration (variant 17) | Cause: single engineer owns core billing system Event: departure without knowledge transfer Impact: extended delivery delays | Third Party & Vendor | Product Delivery | Engineering | risk.owner@example.com | 2025-09-01 | 2026-03-01 | Monitoring | Treat |  | 5 | 2 | 4 | 1 | 1 | 1 | 1.83 | 2 | 3.67 | Low | CTRL-PPL-02 | 2 | 0.24 | 2.79 | Low | Slow | Medium | Cross-train two additional engineers | JIRA-3390 | 2026-05-01 | 10% | Cross-training plan drafted | 2026-01-20 | risk.owner@example.com
RSK-1018 | Upcoming data-residency regulation (variant 18) | Cause: new regional data-residency law Event: non-compliance at enforcement date Impact: regulatory fines and forced re-architecture | Strategic | Data Platform | Legal & Compliance | risk.manager@example.com | 2026-01-05 | 2026-04-05 | Open | Treat |  | 3 | 2 | 3 | 5 | 3 | 1 | 3 | 4 | 12 | High | CTRL-LEG-01 | 1 | 0.12 | 10.56 | Moderate | Medium | High | Data residency compliance program | JIRA-4602 | 2026-03-30 | 15% | Legal assessment underway | 2026-02-01 | risk.manager@example.com
RSK-1019 | Cloud hosting cost overrun (variant 19) | Cause: unbounded auto-scaling configuration Event: unexpected traffic spike Impact: budget overrun | Financial | Cloud Platform | Finance Operations | risk.owner@example.com | 2025-12-01 | 2026-06-01 | Closed | Accept | Cost capped by new billing alerts; residual exposure within appetite | 3 | 1 | 1 | 1 | 1 | 1 | 1.33 | 2 | 2.67 | Low | CTRL-FIN-03 | 4 | 0.48 | 1.39 | Low | Slow | High | Billing alerts and scaling caps implemented | JIRA-4210 | 2026-01-15 | 100% | Controls implemented and verified effective | 2026-01-16 | risk.owner@example.com
RSK-1020 | Single-sourced payment processor outage (variant 20) | Cause: reliance on one payment processor Event: extended processor outage Impact: inability to take customer payments | Operational | Order to Cash | Finance Operations | risk.owner@example.com | 2026-01-10 | 2026-07-10 | Open | Treat |  | 5 | 4 | 3 | 2 | 3 | 1 | 2.83 | 2 | 5.67 | Moderate | CTRL-PAY-01 | 3 | 0.36 | 3.63 | Low | Fast | High | Add secondary payment processor | JIRA-4501 | 2026-04-01 | 30% | Vendor evaluation in progress | 2026-02-05 | risk.manager@example.com